## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
FBUS BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Role Name | In-charge Full Name | Actual Code Iteration | Time: Begin | Time: Deadline | Time: Resit | Note
Register | Register | Medium | Iteration 1 | SE1817 | Le Dang Khoa | Iteration 1 | 2025-06-11 | 2025-06-11 |  | Done
Login | Login | Medium | Iteration 1 | SE1817 | Le Dang Khoa | Iteration 1 | 2025-06-11 | 2025-06-11 |  | Done
Forgot Password | Forgot Password | Medium | Iteration 1 | SE1817 | Mai Quach Kim Tuyen | Iteration 1 | 2025-06-11 | 2025-06-11 |  | Done
Logout | Logout | Simple | Iteration 1 | SE1817 | Mai Quach Kim Tuyen | Iteration 1 | 2025-06-11 | 2025-06-11 |  | Done
Create Account | Manage Accounts | Medium | Iteration 1 | SE1817 | Nguyen Thanh Truong | Iteration 1 | 2025-06-11 | 2025-06-12 |  | Done
View Account | Manage Accounts | Simple | Iteration 1 | SE1817 | Nguyen Thanh Truong | Iteration 1 | 2025-06-12 | 2025-06-12 |  | Done
View Account Details | Manage Accounts | Simple | Iteration 1 | SE1817 | Nguyen Thanh Truong | Iteration 1 | 2025-06-12 | 2025-06-12 |  | Done
Update Account | Manage Accounts | Medium | Iteration 1 | SE1817 | Nguyen Thanh Truong | Iteration 1 | 2025-06-12 | 2025-06-11 |  | Done
View Bookings | Manage Tickets | Medium | Iteration 2 | SE1817 | Tran Thanh Huy | Iteration 2 | 2025-06-13 | 2025-06-18 |  | Done
Cancel Ticket | Manage Tickets | Medium | Iteration 2 | SE1817 | Tran Thanh Huy | Iteration 2 | 2025-06-14 | 2025-06-18 |  | Done
View Profile | Manage Profile | Simple | Iteration 2 | SE1817 | Nguyen Quynh Nhu | Iteration 2 | 2025-06-13 | 2025-06-18 |  | Done
Update Profile | Manage Profile | Medium | Iteration 2 | SE1817 | Nguyen Quynh Nhu | Iteration 2 | 2025-06-14 | 2025-06-18 |  | Done
Change Password | Manage Profile | Medium | Iteration 2 | SE1817 | Nguyen Quynh Nhu | Iteration 2 | 2025-06-15 | 2025-06-18 |  | Done
Assign Driver To Trip | Assign Driver To Trip | Medium | Iteration 2 | SE1817 | Nguyen Thanh Truong | Iteration 2 | 2025-06-16 | 2025-06-19 |  | Done
Manage Bookings | Manage Bookings | Medium | Iteration 2 | SE1817 | Nguyen Thanh Truong | Iteration 2 | 2025-06-16 | 2025-06-19 |  | Done
Create Trip | Manage Trips | Medium | Iteration 2 | SE1817 | Pham Van Hoai | Iteration 2 | 2025-06-16 | 2025-06-19 |  | Done
View Trip Details (Admin) | Manage Trips | Complex | Iteration 2 | SE1817 | Pham Van Hoai | Iteration 2 | 2025-06-17 | 2025-06-18 |  | Done
Update Trip | Manage Trips | Medium | Iteration 2 | SE1817 | Pham Van Hoai | Iteration 2 | 2025-06-17 | 2025-06-18 |  | Done
Delete Trip | Manage Trips | Medium | Iteration 2 | SE1817 | Pham Van Hoai | Iteration 2 | 2025-06-17 | 2025-06-18 |  | Done
Create Bus | Manage Bus Fleet | Medium | Iteration 2 | SE1817 | Tran Thanh Huy | Iteration 2 | 2025-06-16 | 2025-06-19 |  | Done
View Bus Details | Manage Bus Fleet | Simple | Iteration 2 | SE1817 | Tran Thanh Huy | Iteration 2 | 2025-06-17 | 2025-06-19 |  | Done
Update Bus | Manage Bus Fleet | Medium | Iteration 2 | SE1817 | Tran Thanh Huy | Iteration 2 | 2025-06-17 | 2025-06-19 |  | Done
Delete Bus | Manage Bus Fleet | Medium | Iteration 2 | SE1817 | Tran Thanh Huy | Iteration 2 | 2025-06-18 | 2025-06-19 |  | Done
Create Bus Type | Manage Bus Type | Complex | Iteration 2 | SE1817 | Nguyen Quynh Nhu | Iteration 2 | 2025-06-16 | 2025-06-20 |  | Done
View Bus Type Details | Manage Bus Type | Simple | Iteration 2 | SE1817 | Nguyen Quynh Nhu | Iteration 2 | 2025-06-22 | 2025-06-25 |  | Done
Update Bus Type | Manage Bus Type | Complex | Iteration 2 | SE1817 | Nguyen Quynh Nhu | Iteration 2 | 2025-06-19 | 2025-06-25 |  | Done
Delete Bus Type | Manage Bus Type | Medium | Iteration 2 | SE1817 | Nguyen Quynh Nhu | Iteration 2 | 2025-06-18 | 2025-06-21 |  | Done
Support Change Trip for Customer | Support Change Trip for Customer | Medium | Iteration 2 | SE1817 | Mai Quach Kim Tuyen | Iteration 2 | 2025-06-16 | 2025-06-19 |  | Done
Support Cancel Trip for Driver | Support Change Trip for Driver | Medium | Iteration 2 | SE1817 | Mai Quach Kim Tuyen | Iteration 2 | 2025-06-17 | 2025-06-21 |  | Done
Assigned Trips (Driver) | Assigned Trips | Medium | Iteration 2 | SE1817 | Mai Quach Kim Tuyen | Iteration 2 | 2025-06-18 | 2025-06-23 |  | Done
Create Route | Manage Routes | Complex | Iteration 2 | SE1817 | Le Dang Khoa | Iteration 2 | 2025-06-16 | 2025-06-18 |  | Done
View Route Details | Manage Routes | Simple | Iteration 2 | SE1817 | Le Dang Khoa | Iteration 2 | 2025-06-17 | 2025-06-18 |  | Done
Update Route | Manage Routes | Complex | Iteration 2 | SE1817 | Le Dang Khoa | Iteration 2 | 2025-06-18 | 2025-06-19 |  | Done
Delete Route | Manage Routes | Medium | Iteration 2 | SE1817 | Le Dang Khoa | Iteration 2 | 2025-06-18 | 2025-06-19 |  | Done
Create Location | Manage Locations | Medium | Iteration 2 | SE1817 | Pham Van Hoai | Iteration 2 | 2025-06-20 | 2025-06-21 |  | Done
View Location Details | Manage Locations | Simple | Iteration 2 | SE1817 | Pham Van Hoai | Iteration 2 | 2025-06-20 | 2025-06-22 |  | Done
Update Location | Manage Locations | Medium | Iteration 2 | SE1817 | Pham Van Hoai | Iteration 2 | 2025-06-20 | 2025-06-22 |  | Done
Delete Location | Manage Locations | Medium | Iteration 2 | SE1817 | Pham Van Hoai | Iteration 2 | 2025-06-20 | 2025-06-22 |  | Done
View Booking Statistics (Staff) - Dashboard | View Booking Statistics | Complex | Iteration 2 | SE1817 | Nguyen Thanh Truong | Iteration 2 | 2025-06-21 | 2025-06-26 |  | Done
View Booking Detail | View Booking Statistics | Simple | Iteration 2 | SE1817 | Nguyen Thanh Truong | Iteration 2 | 2025-06-21 | 2025-06-23 |  | Done
Print Invoice | View Booking Statistics | Simple | Iteration 2 | SE1817 | Nguyen Thanh Truong | Iteration 2 | 2025-06-26 | 2025-06-29 |  | Done
View Trip List (Home) | View Trip List (Home) | Complex | Iteration 3 | SE1817 | Pham Van Hoai | Iteration 3 | 2025-06-21 | 2025-06-24 |  | Done
Search Ticket(Home) | Search Ticket(Home) | Complex | Iteration 3 | SE1817 | Nguyen Quynh Nhu | Iteration 3 | 2025-06-24 | 2025-06-27 |  | Done
Book Ticket | Book Ticket | Complex | Iteration 3 | SE1817 | Nguyen Thanh Truong | Iteration 3 | 2025-06-26 | 2025-07-01 |  | Done
Request Trip Change | Request Trip Change | Medium | Iteration 3 | SE1817 | Mai Quach Kim Tuyen | Iteration 3 | 2025-06-27 | 2025-07-01 |  | Done
Manage Assigned Trips | Manage Assigned Trips | Medium | Iteration 3 | SE1817 | Mai Quach Kim Tuyen | Iteration 3 | 2025-07-02 | 2025-07-05 |  | Done
View Trip Status | View Trip Status | Medium | Iteration 3 | SE1817 | Le Dang Khoa | Iteration 3 | 2025-06-22 | 2025-06-25 |  | Done
Trip Rating & Review | Manage Tickets | Medium | Iteration 3 | SE1817 | Tran Thanh Huy | Iteration 3 | 2025-06-22 | 2025-07-01 |  | Done
Schedule (Home) | Schedule (Home) | Medium | Iteration 3 | SE1817 | Nguyen Quynh Nhu | Iteration 3 | 2025-06-27 | 2025-07-01 |  | Done
Driver License History | Manage Accounts | Medium | Iteration 3 | SE1817 | Nguyen Thanh Truong | Iteration 3 | 2025-06-26 | 2025-06-29 |  | Done
Admin Statistics | Admin Statistics | Complex | Iteration 3 | SE1817 | Le Dang Khoa | Iteration 3 | 2025-07-03 | 2025-07-10 |  | Done
Staff Invoice Reviews | Staff Invoice Reviews | Simple | Iteration 3 | SE1817 | Tran Thanh Huy | Iteration 3 | 2025-07-06 | 2025-07-11 |  | Done
Driver License | Driver License | Simple | Iteration 3 | SE1817 | Nguyen Quynh Nhu | Iteration 3 | 2025-07-05 | 2025-07-07 |  | Done
Driver Statistic | Driver Statistic | Complex | Iteration 3 | SE1817 | Pham Van Hoai | Iteration 3 | 2025-07-05 | 2025-07-07 |  | Done
Driver Incidents | Driver Incidents | Medium | Iteration 3 | SE1817 | Tran Thanh Huy | Iteration 3 | 2025-07-10 | 2025-07-12 |  | Done
Support Incidents | Support Incidents | Medium | Iteration 3 | SE1817 | Nguyen Quynh Nhu | Iteration 3 | 2025-07-09 | 2025-07-12 |  | Done

## Chuẩn hóa theo LOC (dự kiến) (hidden)
Function Name | Feature | Complexity | In-charge Full Name | Ước lượng LOC | Note
View Trip List | View Trip List | Medium | Pham Van Hoai | 200
View Trip Details | View Trip Details | Medium | Pham Van Hoai | 200
View Booking Statistics (Staff) | View Booking Statistics | Medium | Pham Van Hoai | 250
View Booking Statistics (Admin) | View Statistics | Complex | Pham Van Hoai | 400
Manage Routes (All: CRUD) | Manage Routes | Complex | Pham Van Hoai | 500
Tổng |  |  |  | 1550 | ➕ giao thêm
Manage Bus Type (All: CRUD) | Manage Bus Type | Medium | Pham Van Hoai | 300 | ➕
Tổng sau bổ sung |  |  |  | 1850 | ✅
Function Name | Feature | Complexity | In-charge Full Name | Ước lượng LOC | Note
Create Account | Manage Accounts | Medium | Nguyen Thanh Truong | 250
View Account Details | Manage Accounts | Simple | Nguyen Thanh Truong | 120
Update Account | Manage Accounts | Medium | Nguyen Thanh Truong | 250
Create Trip | Manage Trips | Complex | Nguyen Thanh Truong | 400
View Trip Details (Admin) | Manage Trips | Medium | Nguyen Thanh Truong | 200
Update Trip | Manage Trips | Medium | Nguyen Thanh Truong | 250
Delete Trip | Manage Trips | Medium | Nguyen Thanh Truong | 250
Tổng |  |  |  | 1720 | ➕ giao thêm
Logout | Logout | Simple | Nguyen Thanh Truong | 120
Tổng sau bổ sung |  |  |  | 1840 | ✅
Function Name | Feature | Complexity | In-charge Full Name | Ước lượng LOC | Note
Register | Register | Medium | Le Dang Khoa | 250
Login | Login | Medium | Le Dang Khoa | 250
Change Password | Profile Management | Medium | Le Dang Khoa | 200
Book Ticket | Book Ticket | Complex | Le Dang Khoa | 400
Manage Assigned Trips | Manage Assigned Trips | Complex | Le Dang Khoa | 400
Request Trip Change | Request Trip Change | Medium | Le Dang Khoa | 250
Tổng |  |  |  | 1750 | ➕ giao thêm
Delete Bus Type | Manage Bus Type | Simple | Le Dang Khoa | 100
Tổng sau bổ sung |  |  |  | 1850 | ✅
Function Name | Feature | Complexity | In-charge Full Name | Ước lượng LOC | Note
Forgot Password | Forgot Password | Medium | Tran Thanh Huy | 200
View Profile | Profile Management | Simple | Tran Thanh Huy | 120
Update Profile | Profile Management | Medium | Tran Thanh Huy | 200
View Bus Details | Manage Bus Fleet | Medium | Tran Thanh Huy | 200
Update Bus | Manage Bus Fleet | Medium | Tran Thanh Huy | 200
Delete Bus | Manage Bus Fleet | Medium | Tran Thanh Huy | 200
Support Change Trip for Driver | Support Trip (Driver) | Medium | Tran Thanh Huy | 250
Tổng |  |  |  | 1370 | ➕ giao thêm
Create Bus | Manage Bus Fleet | Complex | Tran Thanh Huy | 400
Tổng sau bổ sung |  |  |  | 1770 | ✅
Function Name | Feature | Complexity | In-charge Full Name | Ước lượng LOC | Note
View Bookings | Ticket Management | Medium | Mai Quach Kim Tuyen | 200
Cancel Ticket | Ticket Management | Medium | Mai Quach Kim Tuyen | 200
Assign Driver To Trip | Assign Driver | Complex | Mai Quach Kim Tuyen | 400
Support Change Trip for Customer | Support Trip (Customer) | Medium | Mai Quach Kim Tuyen | 250
Delete Account | Manage Accounts | Medium | Mai Quach Kim Tuyen | 250
View Route Details | Manage Routes | Medium | Mai Quach Kim Tuyen | 200
Tổng |  |  |  | 1500 | ➕ giao thêm
Delete Route | Manage Routes | Medium | Mai Quach Kim Tuyen | 250
Tổng sau bổ sung |  |  |  | 1750 | ✅
Function Name | Feature | Complexity | In-charge Full Name | Ước lượng LOC | Note
View Bus Type Details | Manage Bus Type | Medium | Nguyen Quynh Nhu | 200
Update Bus Type | Manage Bus Type | Medium | Nguyen Quynh Nhu | 200
Create Route | Manage Routes | Medium | Nguyen Quynh Nhu | 250
Update Route | Manage Routes | Medium | Nguyen Quynh Nhu | 250
Delete Bus | Manage Bus Fleet | Medium | Nguyen Quynh Nhu | 200
Delete Account | Manage Accounts | Medium | Nguyen Quynh Nhu | 250
Tổng |  |  |  | 1350 | ➕ giao thêm
Create Bus Type | Manage Bus Type | Medium | Nguyen Quynh Nhu | 250
Tổng sau bổ sung |  |  |  | 1600 | ✅

## Group_Contribution
Họ và tên | Tỉ lệ đóng góp | Mô tả
Phạm Văn Hoài | 19% | Quản lý source code Thiết kế giao diện Xử lí nghiệp vụ chức năng Thiết kế cơ sở dữ liệu
Nguyễn Thành Trương | 19% | Thiết kế giao diện Xử lí nghiệp vụ chức năng Giám sát tài liệu Đánh giá quá trình
Lê Đăng Khoa | 17% | Thiết kế giao diện Xử lí nghiệp vụ chức năng Giám sát tài liệu Đánh giá quá trình
Mai Quách Kim Tuyền | 15% | Thiết kế giao diện Xử lí nghiệp vụ chức năng Thiết kế tài liệu
Nguyễn Quỳnh Như | 15% | Thiết kế giao diện Xử lí nghiệp vụ chức năng Thiết kế tài liệu
Trần Thanh Huy | 15% | Thiết kế giao diện Xử lí nghiệp vụ chức năng Phá tài liệu